## Sheet1
Date | Task (Project)/Note/Priority | Urgent | Today’s Target | Time |  | Deadline | Complexity | Status | Performance remark | [5 empty] | Comment/Suggestion by PL | Comments by Developer
|  | Y/N |  | E | A |  | H/M/S |  | RU | C | L | SI | HC | Total
30th Nov 12
29th Nov 12
28th Nov 12
27th Nov 12
26th Nov 12
24th Nov 12
23rd Nov 12
22nd Nov 12
21st Nov 12
20th Nov 12
19th Nov 12
17th Nov 12
16th Nov
12th Nov 12 | Flexiprint – Drag Issue | y | 100% | 3 | 5 | Today | S | 100% | 1 | 1 | 1 | 1 | 1 |  | Completed the tasks as suggested. Needs to speed up.
10th Nov 12 | No Daily sheet
9th Nov 12 | Flexiw2p – Update sent by Mr. Nicu | y | 100% | 8 | 6 | Today | S | 100% | 1 | 1 | 1 | 1 | 1 |  | Completed the work as sugested. Needs to speed up.
8th Nov 12 | Flexiprint – Speed issue – R n D | y | 100% | 8 | 6 | Today | M | 50% | 1 | 1 | 1 | 1 | 1 |  | Working on the changes. Completed the tasks as suggested.
7th Nov 12 | Flexiw2p – Changes sent by Mr. Nicu | y | 100% | 0.5 | 0.5 | Today | S | 100% | 1 | 1 | 1 | 1 | 1 |  | Simple html related work. Completed the task as suggsted.
| Palace Resor My Account Page Updates | Y | 100% | 2 |  |  | M | 80% | 1 | 1 | 1 | 1 | 1 |  | Done the work but taken too much time. Have to improve the joomla page finding logic.
6th Nov 12 | Flexiprint – Fotolia Integration – Uploading | y | 100% | 4 | 2 | Today | M | 50% | 1 | 1 | 1 | 1 | 1 |  | Needs to improve his speed.
| Flexiw2p – Changes sent by Mr. Nicu | y | 100% | 4 | 4 | Today | S | 100% | 1 | 1 | 1 | 1 | 1 |  | Good Work. Completed the tasks as suggested.
5th Nov 12 | Flexiw2p – Payment Gateway Changes | y | 100% | 4 | 7 | Today | S | 100% | 1 | 1 | 1 | 0 | 1 |  | Completed the tasks as suggested. Needs to improve the pace in which he completes the work.
2nd Nov 12 | Flexiw2p – Online Mart Issue Solving | y | 100% | 2 | 2 | Today | S | 100% | 1 | 1 | 1 | 1 | 1 |  | Completed the task as suggsted.
| Javascript Editor – Editable Text Popup Issue | y | 100% | 2 | 2 | Today | M | 100% | 1 | 1 | 1 | 1 | 1 |  | Solved the issue related to the text popup.
| Javascript Editor – Upload Functionalities | y | 100% | 4 |  | Today | M | 50% | 1 | 1 | 1 | 1 | 1
1st Nov 12 | Flexiw2p – Uploading of Online Mart Functionalities on the live server. | y | 100% | 2 | 2 | Today | S | 100% | 1 | 1 | 1 | 1 | 1
| Flexiw2p – Online Mart Issue Solving | y | 100% | 6 | 6 | Today | S | 60% | 0 | 1 | 1 | 0 | 1 |  | Was very slow, in whatever changes done today. Even after giving proper instructions.
Note on C34: Hemkant
Note on C38: Hemkant
Note on C40: Hemkant
Note on C42: Hemkant
Note on C43: Shoaib
Note on C45: Hemkant
Note on C46: Hemkant
Note on C48: Hemkant
Note on C50: Hemkant
Note on C51: Hemkant
Note on C52: Hemkant
Note on C54: Hemkant
Note on C55: Hemkant